## Project Plan
| Resource | Wk1 | Wk2 | Wk3 | Wk4 | Wk5 | Wk6 | Wk7 | Wk8 | Wk 9 | Wk 10 | Wk 11 | Wk 12
Pre Dev
Review and Sign off on scope/wireframes | Team
Staffing project/ramp up | Tech Lead
High level Architecture | Senior Back End Dev/Senior Front End Dev
Procure dev/test/cert/prod envrionments | Operations
Build scripts version control, CI | Senior Backend Dev Operations
Dev
PSD | Designer
Static HTML | Frontend HTML/CSS
DB Design | Senior Back End Dev
Integrate Existing Data | Senior Back End Dev
Test Plab Development
Profile
API Design | Senior Back End Dev/Senior Front End Dev
API Development | Senior Back End Dev
Front End JS Services (Profile) + Mocks | Senior Front End Developer
Front End form development (validation rules, state management) | Senior Front End Developer
API Integration | Senior Back End Dev/Senior Front End Dev
Testing | QA
Revisions | Senior Back End Dev/Senior Front End Dev
Deploy to cert | Operations
Demo and Client Sign off | Team
Forest Land Info
API Design | Senior Back End Dev/Senior Front End Dev
API Development | Senior Back End Dev
Front End JS Services (Profile) + Mocks | Senior Front End Developer
Front End form development (validation rules, state management) | Senior Front End Developer
API Integration | Senior Back End Dev/Senior Front End Dev
Testing | QA
Revisions | Senior Back End Dev/Senior Front End Dev
Deploy to cert | Operations
Demo and Client Sign off | Team
Performance Testing Hardeing
Run performance tests | QA
Monitor | Operations
Optimize | Senior Back End Dev/Senior Front End Dev
Deploy to cert | Operations
Demo and Client Sign off | Team
Go live | Operations

## Resources
RESOURCES
Insight Action Inc
Designer (1 Week FT - then 1 week spread over course of project)
Tech Lead/ Scrum Master/Project Manager (FT Deidicated)
Senior Back End Developer - responsible for data design, API Support
Senior Front end Developer (Angular)
HTML/CSS developer FT front loaded - then 20% in supporting role as required
DBA - PT for code review and tuning
QA
Client
Client - Product Sposnsor
Client - Technical Conatact

## Assumptions
ASSUMPTIONS
What we need from client
All techincal discovery is completes and integration points are well understood
If there is a company style guide that needs to be followed it will be provided prior to commencenment.
No techincal constraints regarding choices of DB, Middleware front end stack.
If there are techincal constraints they will be known prior to sign off on scope
All existing data will be provided in CSV format prior to project start.
Application Assumptions
Only Supporting One language
User is already logged into the system (no SSO integartion or authentication requirements)
Scale of data is known and small enough not to require special cosnideration
Staffing…
Tech lead acts as PM scrum master and provides added development badnwidth. Rate is blended with otehr development costs.
If we need to work with techincal staff on client side theymust be made available as required
Client will make product owner available for clarifiactun during process and periodic demo/review sessions